## Gantt
Task Order 60 Project | [20 empty] | Project Timespan: | [6 empty] | 2024-01-11 |  |  |  | - | 2024-02-20 |  |  |  | (29) |  |  |  |  | Project Manager: | [5 empty] | B. Prisock | [9 empty] | Settings
| Input Column | [6 empty] | Auto Stage ind. Start |  |  | =MIN(ITEMS_START) | [9 empty] | Color By | [8 empty] | Display | [9 empty] | Show Progress
| Calculated Column | [6 empty] | Auto Stage workdays |  |  | =NETWORKDAYS(plan_start, MAX(<items_end>)) | [9 empty] | Project Structure | [8 empty] | Plan vs Base | [9 empty] | No
Snapshot Column
⚠, ◆, ⚑, ↖, ↙ | [7 empty] | Acutal Plan | [9 empty] | Base Plan | time axis 2024-01-08 to 2024-03-29
[8 empty] | Updated on: | [9 empty] | Saved on: |  | 40
Ids |  |  | Item Details
id | s Id | r id | Type | Description | Role | Team Member | ⚠ | ind. Start | ind. End | d. id | d. item |  | d. conn | d. lag | FTE | Start | End | Start | End | % | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | 1 | -1 | S | Planning |  |  |  | 2024-01-11 |  |  |  |  | FS |  | 15 | 2024-01-11 | 2024-01-31 | 2024-01-04 | 2024-01-16
2 | 1 | 1 | T | Create Design UC | PM | GES |  | 2024-01-11 |  |  |  |  | FS |  | 5 | 2024-01-11 | 2024-01-17 | 2024-01-04 | 2024-01-10
3 | 1 | 1 | T | Task P2 | PM | GES |  |  |  | 2 | ↖ | (T)Create … | FS |  | 5 | 2024-01-18 | 2024-01-24 | 2024-01-11 | 2024-01-15
4 | 1 | 4 | T | Task P3 | MAR | GLOMA |  |  |  | 3 | ↖ | (T)Task P2 | FF |  | 2 | 2024-01-23 | 2024-01-24 | 2024-01-12 | 2024-01-15
5 | 1 | 4 | T | Task P4 | MAR | GLOMA |  |  |  | 4 | ↖ | (T)Task P3 | FS |  | 5 | 2024-01-25 | 2024-01-31 | 2024-01-16 | 2024-01-16
6 | 1 | -1 | M | Milestone 1 | [5 empty] | 5 | ↖ | (T)Task P4 | FF |  |  | 2024-01-31 | 2024-01-31 | 2024-01-16 | 2024-01-16 | bar: 2024-01-16; 2024-01-31
7 | 2 | -1 | S | Implementation |  |  |  | 2024-01-25 |  |  |  |  | FS |  | 8 | 2024-01-25 | 2024-02-05 | 2024-01-16 | 2024-02-02
8 | 2 | -1 | T | Task I1 | [5 empty] | 1 | ↖ | (S)Plannin… | FF |  | 5 | 2024-01-25 | 2024-01-31 | 2024-01-17 | 2024-01-23
9 | 2 | -1 | T | Task I2 | [8 empty] | FS |  | 6 |  |  | 2024-01-16 | 2024-01-23
10 | 3 | -1 | S | Task I3 | [5 empty] | 4 | ↖ | (T)Task P3 | FS |  | 2 | 2024-01-25 | 2024-01-26 | 2024-01-24 | 2024-01-25
11 | 3 | -1 | T | Task I4 | [5 empty] | 10 | ↖ | (S)Task I3 | FS |  | 6 | 2024-01-29 | 2024-02-05 | 2024-01-26 | 2024-02-02
12 | 3 | -1 | M | Milestone 2 | [5 empty] | 11 | ↖ | (T)Task I4 | FF |  |  | 2024-02-05 | 2024-02-05 | 2024-02-02 | 2024-02-02 | bar: 2024-02-02 to 2024-02-05
13 | 3 | -1 | T | Task I5 | [5 empty] | 12 | ↖ | (M)Milesto… | FS |  |  | 2024-02-06 | 2024-02-06 | 2024-02-05 | 2024-02-05
14 | 3 | -1 | M | Milestone 3 | [5 empty] | 13 | ↖ | (T)Task I5 | FS |  |  | 2024-02-07 | 2024-02-07 | 2024-02-06 | 2024-02-06 | bar: 2024-02-06 to 2024-02-07
15 | 4 | -1 | S | Rollout Prep |  |  |  | 2024-01-29 |  |  |  |  | FS |  | 11 | 2024-01-29 | 2024-02-12 | 2024-01-09 | 2024-01-23
16 | 4 | -1 | T | Task RP1 | [5 empty] | 10 | ↖ | (S)Task I3 | FS |  | 5 | 2024-01-29 | 2024-02-02 | 2024-01-09 | 2024-01-15
17 | 4 | -1 | T | Task RP2 | [5 empty] | 16 | ↖ | (T)Task RP… | FS |  | 4 | 2024-02-05 | 2024-02-08 | 2024-01-16 | 2024-01-19
18 | 4 | -1 | T | Task RP3 | [5 empty] | 17 | ↖ | (T)Task RP… | FS |  | 2 | 2024-02-09 | 2024-02-12 | 2024-01-22 | 2024-01-23
19 | 4 | -1 | M | Milestone 4 | [5 empty] | 18 | ↖ | (T)Task RP… | FF |  |  | 2024-02-12 | 2024-02-12 | 2024-01-23 | 2024-01-23 | bar: 2024-01-23; 2024-02-12
20 | 5 | -1 | S | Rollout |  |  |  | 2024-02-13 |  |  |  |  | FS |  | 6 | 2024-02-13 | 2024-02-20 | 2024-01-24 | 2024-01-31
21 | 5 | -1 | T | task r1 | [5 empty] | 15 | ↖ | (S)Rollout… | FS |  | 6 | 2024-02-13 | 2024-02-20 | 2024-01-24 | 2024-01-31
22 | [12 empty] | FS
23 | [12 empty] | FS
24 | [12 empty] | FS
25 | [12 empty] | FS
26 | [12 empty] | FS
27 | [12 empty] | FS
28 | [12 empty] | FS
29 | [12 empty] | FS
30 | [12 empty] | FS
31 | [12 empty] | FS
32 | [12 empty] | FS
33 | [12 empty] | FS
34 | [12 empty] | FS
35 | [12 empty] | FS
36 | [12 empty] | FS
37 | [12 empty] | FS
38 | [12 empty] | FS
39 | [12 empty] | FS
40 | [12 empty] | FS
41 | [12 empty] | FS
42 | [12 empty] | FS
43 | [12 empty] | FS
44 | [12 empty] | FS
45 | [12 empty] | FS
46 | [12 empty] | FS
47 | [12 empty] | FS
48 | [12 empty] | FS
49 | [12 empty] | FS
50 | [12 empty] | FS
51 | [12 empty] | FS
52 | [12 empty] | FS
53 | [12 empty] | FS
54 | [12 empty] | FS
55 | [12 empty] | FS
56 | [12 empty] | FS
57 | [12 empty] | FS
58 | [12 empty] | FS
59 | [12 empty] | FS
60 | [12 empty] | FS
61 | [12 empty] | FS
62 | [12 empty] | FS
63 | [12 empty] | FS
64 | [12 empty] | FS
65 | [12 empty] | FS
66 | [12 empty] | FS
67 | [12 empty] | FS
68 | [12 empty] | FS
69 | [12 empty] | FS
70 | [12 empty] | FS
71 | [12 empty] | FS
72 | [12 empty] | FS
73 | [12 empty] | FS
74 | [12 empty] | FS
75 | [12 empty] | FS
76 | [12 empty] | FS
77 | [12 empty] | FS
78 | [12 empty] | FS
79 | [12 empty] | FS
80 | [12 empty] | FS
81 | [12 empty] | FS
82 | [12 empty] | FS
83 | [12 empty] | FS
84 | [12 empty] | FS
85 | [12 empty] | FS
86 | [12 empty] | FS
87 | [12 empty] | FS
88 | [12 empty] | FS
89 | [12 empty] | FS
90 | [12 empty] | FS
91 | [12 empty] | FS
92 | [12 empty] | FS
93 | [12 empty] | FS
94 | [12 empty] | FS
95 | [12 empty] | FS
96 | [12 empty] | FS
97 | [12 empty] | FS
98 | [12 empty] | FS
99 | [12 empty] | FS
100 | [12 empty] | FS
101 | [12 empty] | FS
102 | [12 empty] | FS
103 | [12 empty] | FS
104 | [12 empty] | FS
105 | [12 empty] | FS
106 | [12 empty] | FS
107 | [12 empty] | FS
108 | [12 empty] | FS
109 | [12 empty] | FS
110 | [12 empty] | FS
111 | [12 empty] | FS
112 | [12 empty] | FS
113 | [12 empty] | FS
114 | [12 empty] | FS
115 | [12 empty] | FS
116 | [12 empty] | FS
117 | [12 empty] | FS
118 | [12 empty] | FS
119 | [12 empty] | FS
120 | [12 empty] | FS
121 | [12 empty] | FS
122 | [12 empty] | FS
123 | [12 empty] | FS
124 | [12 empty] | FS
125 | [12 empty] | FS
126 | [12 empty] | FS
127 | [12 empty] | FS
128 | [12 empty] | FS
129 | [12 empty] | FS
130 | [12 empty] | FS
131 | [12 empty] | FS
132 | [12 empty] | FS
133 | [12 empty] | FS
134 | [12 empty] | FS
135 | [12 empty] | FS
136 | [12 empty] | FS
137 | [12 empty] | FS
138 | [12 empty] | FS
139 | [12 empty] | FS
140 | [12 empty] | FS
141 | [12 empty] | FS
142 | [12 empty] | FS
143 | [12 empty] | FS
144 | [12 empty] | FS
145 | [12 empty] | FS
146 | [12 empty] | FS
147 | [12 empty] | FS
148 | [12 empty] | FS
149 | [12 empty] | FS
150 | [12 empty] | FS
151 | [12 empty] | FS
152 | [12 empty] | FS
153 | [12 empty] | FS
154 | [12 empty] | FS
155 | [12 empty] | FS
156 | [12 empty] | FS
157 | [12 empty] | FS
158 | [12 empty] | FS
159 | [12 empty] | FS
160 | [12 empty] | FS
161 | [12 empty] | FS
162 | [12 empty] | FS
163 | [12 empty] | FS
164 | [12 empty] | FS
165 | [12 empty] | FS
166 | [12 empty] | FS
167 | [12 empty] | FS
168 | [12 empty] | FS
169 | [12 empty] | FS
170 | [12 empty] | FS
171 | [12 empty] | FS
172 | [12 empty] | FS
173 | [12 empty] | FS
174 | [12 empty] | FS
175 | [12 empty] | FS
176 | [12 empty] | FS
177 | [12 empty] | FS
178 | [12 empty] | FS
179 | [12 empty] | FS
180 | [12 empty] | FS
181 | [12 empty] | FS
182 | [12 empty] | FS
183 | [12 empty] | FS
184 | [12 empty] | FS
185 | [12 empty] | FS
186 | [12 empty] | FS
187 | [12 empty] | FS
188 | [12 empty] | FS
189 | [12 empty] | FS
190 | [12 empty] | FS
191 | [12 empty] | FS
192 | [12 empty] | FS
193 | [12 empty] | FS
194 | [12 empty] | FS
195 | [12 empty] | FS
196 | [12 empty] | FS
197 | [12 empty] | FS
198 | [12 empty] | FS
199 | [12 empty] | FS
200 | [12 empty] | FS
201 | [12 empty] | FS
202 | [12 empty] | FS
203 | [12 empty] | FS
204 | [12 empty] | FS
205 | [12 empty] | FS
206 | [12 empty] | FS
207 | [12 empty] | FS
208 | [12 empty] | FS
209 | [12 empty] | FS
210 | [12 empty] | FS
211 | [12 empty] | FS
212 | [12 empty] | FS
213 | [12 empty] | FS
214 | [12 empty] | FS
215 | [12 empty] | FS
216 | [12 empty] | FS
217 | [12 empty] | FS
218 | [12 empty] | FS
219 | [12 empty] | FS
220 | [12 empty] | FS
221 | [12 empty] | FS
222 | [12 empty] | FS
223 | [12 empty] | FS
224 | [12 empty] | FS
225 | [12 empty] | FS
226 | [12 empty] | FS
227 | [12 empty] | FS
228 | [12 empty] | FS
229 | [12 empty] | FS
230 | [12 empty] | FS
231 | [12 empty] | FS
232 | [12 empty] | FS
233 | [12 empty] | FS
234 | [12 empty] | FS
235 | [12 empty] | FS
236 | [12 empty] | FS
237 | [12 empty] | FS
238 | [12 empty] | FS
239 | [12 empty] | FS
240 | [12 empty] | FS
241 | [12 empty] | FS
242 | [12 empty] | FS
243 | [12 empty] | FS
244 | [12 empty] | FS
245 | [12 empty] | FS
246 | [12 empty] | FS
247 | [12 empty] | FS
248 | [12 empty] | FS
249 | [12 empty] | FS
250 | [12 empty] | FS
251 | [12 empty] | FS
252 | [12 empty] | FS
253 | [12 empty] | FS
254 | [12 empty] | FS
255 | [12 empty] | FS
256 | [12 empty] | FS
257 | [12 empty] | FS
258 | [12 empty] | FS
259 | [12 empty] | FS
260 | [12 empty] | FS
261 | [12 empty] | FS
262 | [12 empty] | FS
263 | [12 empty] | FS
264 | [12 empty] | FS
265 | [12 empty] | FS
266 | [12 empty] | FS
267 | [12 empty] | FS
268 | [12 empty] | FS
269 | [12 empty] | FS
270 | [12 empty] | FS
271 | [12 empty] | FS
272 | [12 empty] | FS
273 | [12 empty] | FS
274 | [12 empty] | FS
275 | [12 empty] | FS
276 | [12 empty] | FS
277 | [12 empty] | FS
278 | [12 empty] | FS
279 | [12 empty] | FS
280 | [12 empty] | FS
281 | [12 empty] | FS
282 | [12 empty] | FS
283 | [12 empty] | FS
284 | [12 empty] | FS
285 | [12 empty] | FS
286 | [12 empty] | FS
287 | [12 empty] | FS
288 | [12 empty] | FS
289 | [12 empty] | FS
290 | [12 empty] | FS
291 | [12 empty] | FS
292 | [12 empty] | FS
293 | [12 empty] | FS
294 | [12 empty] | FS
295 | [12 empty] | FS
296 | [12 empty] | FS
297 | [12 empty] | FS
298 | [12 empty] | FS
299 | [12 empty] | FS
300 | [12 empty] | FS
301 | [12 empty] | FS
302 | [12 empty] | FS
303 | [12 empty] | FS
304 | [12 empty] | FS
305 | [12 empty] | FS
306 | [12 empty] | FS
307 | [12 empty] | FS
308 | [12 empty] | FS
309 | [12 empty] | FS
310 | [12 empty] | FS
311 | [12 empty] | FS
312 | [12 empty] | FS
313 | [12 empty] | FS
314 | [12 empty] | FS
315 | [12 empty] | FS
316 | [12 empty] | FS
317 | [12 empty] | FS
318 | [12 empty] | FS
319 | [12 empty] | FS
320 | [12 empty] | FS
321 | [12 empty] | FS
322 | [12 empty] | FS
323 | [12 empty] | FS
324 | [12 empty] | FS
325 | [12 empty] | FS
326 | [12 empty] | FS
327 | [12 empty] | FS
328 | [12 empty] | FS
329 | [12 empty] | FS
330 | [12 empty] | FS
331 | [12 empty] | FS
332 | [12 empty] | FS
333 | [12 empty] | FS
334 | [12 empty] | FS
335 | [12 empty] | FS
336 | [12 empty] | FS
337 | [12 empty] | FS
338 | [12 empty] | FS
339 | [12 empty] | FS
340 | [12 empty] | FS
341 | [12 empty] | FS
342 | [12 empty] | FS
343 | [12 empty] | FS
344 | [12 empty] | FS
345 | [12 empty] | FS
346 | [12 empty] | FS
347 | [12 empty] | FS
348 | [12 empty] | FS
349 | [12 empty] | FS
350 | [12 empty] | FS
351 | [12 empty] | FS
352 | [12 empty] | FS
353 | [12 empty] | FS
354 | [12 empty] | FS
355 | [12 empty] | FS
356 | [12 empty] | FS
357 | [12 empty] | FS
358 | [12 empty] | FS
359 | [12 empty] | FS
360 | [12 empty] | FS
361 | [12 empty] | FS
362 | [12 empty] | FS
363 | [12 empty] | FS
364 | [12 empty] | FS
365 | [12 empty] | FS
366 | [12 empty] | FS
367 | [12 empty] | FS
368 | [12 empty] | FS
369 | [12 empty] | FS
370 | [12 empty] | FS
371 | [12 empty] | FS
372 | [12 empty] | FS
373 | [12 empty] | FS
374 | [12 empty] | FS
375 | [12 empty] | FS
376 | [12 empty] | FS
377 | [12 empty] | FS
378 | [12 empty] | FS
379 | [12 empty] | FS
380 | [12 empty] | FS
381 | [12 empty] | FS
382 | [12 empty] | FS
383 | [12 empty] | FS
384 | [12 empty] | FS
385 | [12 empty] | FS
386 | [12 empty] | FS
387 | [12 empty] | FS
388 | [12 empty] | FS
389 | [12 empty] | FS
390 | [12 empty] | FS
391 | [12 empty] | FS
392 | [12 empty] | FS
393 | [12 empty] | FS
394 | [12 empty] | FS
395 | [12 empty] | FS
396 | [12 empty] | FS
397 | [12 empty] | FS
398 | [12 empty] | FS
399 | [12 empty] | FS
400 | [12 empty] | FS
401 | [12 empty] | FS
402 | [12 empty] | FS
403 | [12 empty] | FS
404 | [12 empty] | FS
405 | [12 empty] | FS
406 | [12 empty] | FS
407 | [12 empty] | FS
408 | [12 empty] | FS
409 | [12 empty] | FS
410 | [12 empty] | FS
411 | [12 empty] | FS
412 | [12 empty] | FS
413 | [12 empty] | FS
414 | [12 empty] | FS
415 | [12 empty] | FS
416 | [12 empty] | FS
417 | [12 empty] | FS
418 | [12 empty] | FS
419 | [12 empty] | FS
420 | [12 empty] | FS
421 | [12 empty] | FS
422 | [12 empty] | FS
423 | [12 empty] | FS
424 | [12 empty] | FS
425 | [12 empty] | FS
426 | [12 empty] | FS
427 | [12 empty] | FS
428 | [12 empty] | FS
429 | [12 empty] | FS
430 | [12 empty] | FS
431 | [12 empty] | FS
432 | [12 empty] | FS
433 | [12 empty] | FS
434 | [12 empty] | FS
435 | [12 empty] | FS
436 | [12 empty] | FS
437 | [12 empty] | FS
438 | [12 empty] | FS
439 | [12 empty] | FS
440 | [12 empty] | FS
441 | [12 empty] | FS
442 | [12 empty] | FS
443 | [12 empty] | FS
444 | [12 empty] | FS
445 | [12 empty] | FS
446 | [12 empty] | FS
447 | [12 empty] | FS
448 | [12 empty] | FS
449 | [12 empty] | FS
450 | [12 empty] | FS
451 | [12 empty] | FS
452 | [12 empty] | FS
453 | [12 empty] | FS
454 | [12 empty] | FS
455 | [12 empty] | FS
456 | [12 empty] | FS
457 | [12 empty] | FS
458 | [12 empty] | FS
459 | [12 empty] | FS
460 | [12 empty] | FS
461 | [12 empty] | FS
462 | [12 empty] | FS
463 | [12 empty] | FS
464 | [12 empty] | FS
465 | [12 empty] | FS
466 | [12 empty] | FS
467 | [12 empty] | FS
468 | [12 empty] | FS
469 | [12 empty] | FS
470 | [12 empty] | FS
471 | [12 empty] | FS
472 | [12 empty] | FS
473 | [12 empty] | FS
474 | [12 empty] | FS
475 | [12 empty] | FS
476 | [12 empty] | FS
477 | [12 empty] | FS
478 | [12 empty] | FS
479 | [12 empty] | FS
480 | [12 empty] | FS
481 | [12 empty] | FS
482 | [12 empty] | FS
483 | [12 empty] | FS
484 | [12 empty] | FS
485 | [12 empty] | FS
486 | [12 empty] | FS
487 | [12 empty] | FS
488 | [12 empty] | FS
489 | [12 empty] | FS
490 | [12 empty] | FS
491 | [12 empty] | FS
492 | [12 empty] | FS
493 | [12 empty] | FS
494 | [12 empty] | FS
495 | [12 empty] | FS
496 | [12 empty] | FS
497 | [12 empty] | FS
498 | [12 empty] | FS
499 | [12 empty] | FS
500 | [12 empty] | FS
501 | [12 empty] | FS
502 | [12 empty] | FS
503 | [12 empty] | FS
504 | [12 empty] | FS
505 | [12 empty] | FS
506 | [12 empty] | FS
507 | [12 empty] | FS
508 | [12 empty] | FS
509 | [12 empty] | FS
510 | [12 empty] | FS
511 | [12 empty] | FS
512 | [12 empty] | FS
513 | [12 empty] | FS
514 | [12 empty] | FS
515 | [12 empty] | FS
516 | [12 empty] | FS
517 | [12 empty] | FS
518 | [12 empty] | FS
519 | [12 empty] | FS
520 | [12 empty] | FS
521 | [12 empty] | FS
522 | [12 empty] | FS
523 | [12 empty] | FS
524 | [12 empty] | FS
525 | [12 empty] | FS
526 | [12 empty] | FS
527 | [12 empty] | FS
528 | [12 empty] | FS
529 | [12 empty] | FS
530 | [12 empty] | FS
531 | [12 empty] | FS
532 | [12 empty] | FS
533 | [12 empty] | FS
534 | [12 empty] | FS
535 | [12 empty] | FS
536 | [12 empty] | FS
537 | [12 empty] | FS
538 | [12 empty] | FS
539 | [12 empty] | FS
540 | [12 empty] | FS
541 | [12 empty] | FS
542 | [12 empty] | FS
543 | [12 empty] | FS
544 | [12 empty] | FS
545 | [12 empty] | FS
546 | [12 empty] | FS
547 | [12 empty] | FS
548 | [12 empty] | FS
549 | [12 empty] | FS
550 | [12 empty] | FS
551 | [12 empty] | FS
552 | [12 empty] | FS
553 | [12 empty] | FS
554 | [12 empty] | FS
555 | [12 empty] | FS
556 | [12 empty] | FS
557 | [12 empty] | FS
558 | [12 empty] | FS
559 | [12 empty] | FS
560 | [12 empty] | FS
561 | [12 empty] | FS
562 | [12 empty] | FS
563 | [12 empty] | FS
564 | [12 empty] | FS
565 | [12 empty] | FS
566 | [12 empty] | FS
567 | [12 empty] | FS
568 | [12 empty] | FS
569 | [12 empty] | FS
570 | [12 empty] | FS
571 | [12 empty] | FS
572 | [12 empty] | FS
573 | [12 empty] | FS
574 | [12 empty] | FS
575 | [12 empty] | FS
576 | [12 empty] | FS
577 | [12 empty] | FS
578 | [12 empty] | FS
579 | [12 empty] | FS
580 | [12 empty] | FS
581 | [12 empty] | FS
582 | [12 empty] | FS
583 | [12 empty] | FS
584 | [12 empty] | FS
585 | [12 empty] | FS
586 | [12 empty] | FS
587 | [12 empty] | FS
588 | [12 empty] | FS
589 | [12 empty] | FS
590 | [12 empty] | FS
591 | [12 empty] | FS
592 | [12 empty] | FS
593 | [12 empty] | FS
594 | [12 empty] | FS
595 | [12 empty] | FS
596 | [12 empty] | FS
597 | [12 empty] | FS
598 | [12 empty] | FS
599 | [12 empty] | FS
600 | [12 empty] | FS
601 | [12 empty] | FS
602 | [12 empty] | FS
603 | [12 empty] | FS
604 | [12 empty] | FS
605 | [12 empty] | FS
606 | [12 empty] | FS
607 | [12 empty] | FS
608 | [12 empty] | FS
609 | [12 empty] | FS
610 | [12 empty] | FS
611 | [12 empty] | FS
612 | [12 empty] | FS
613 | [12 empty] | FS
614 | [12 empty] | FS
615 | [12 empty] | FS
616 | [12 empty] | FS
617 | [12 empty] | FS
618 | [12 empty] | FS
619 | [12 empty] | FS
620 | [12 empty] | FS
621 | [12 empty] | FS
622 | [12 empty] | FS
623 | [12 empty] | FS
624 | [12 empty] | FS
625 | [12 empty] | FS
626 | [12 empty] | FS
627 | [12 empty] | FS
628 | [12 empty] | FS
629 | [12 empty] | FS
630 | [12 empty] | FS
631 | [12 empty] | FS
632 | [12 empty] | FS
633 | [12 empty] | FS
634 | [12 empty] | FS
635 | [12 empty] | FS
636 | [12 empty] | FS
637 | [12 empty] | FS
638 | [12 empty] | FS
639 | [12 empty] | FS
640 | [12 empty] | FS
641 | [12 empty] | FS
642 | [12 empty] | FS
643 | [12 empty] | FS
644 | [12 empty] | FS
645 | [12 empty] | FS
646 | [12 empty] | FS
647 | [12 empty] | FS
648 | [12 empty] | FS
649 | [12 empty] | FS
650 | [12 empty] | FS
651 | [12 empty] | FS
652 | [12 empty] | FS
653 | [12 empty] | FS
654 | [12 empty] | FS
655 | [12 empty] | FS
656 | [12 empty] | FS
657 | [12 empty] | FS
658 | [12 empty] | FS
659 | [12 empty] | FS
660 | [12 empty] | FS
661 | [12 empty] | FS
662 | [12 empty] | FS
663 | [12 empty] | FS
664 | [12 empty] | FS
665 | [12 empty] | FS
666 | [12 empty] | FS
667 | [12 empty] | FS
668 | [12 empty] | FS
669 | [12 empty] | FS
670 | [12 empty] | FS
671 | [12 empty] | FS
672 | [12 empty] | FS
673 | [12 empty] | FS
674 | [12 empty] | FS
675 | [12 empty] | FS
676 | [12 empty] | FS
677 | [12 empty] | FS
678 | [12 empty] | FS
679 | [12 empty] | FS
680 | [12 empty] | FS
681 | [12 empty] | FS
682 | [12 empty] | FS
683 | [12 empty] | FS
684 | [12 empty] | FS
685 | [12 empty] | FS
686 | [12 empty] | FS
687 | [12 empty] | FS
688 | [12 empty] | FS
689 | [12 empty] | FS
690 | [12 empty] | FS
691 | [12 empty] | FS
692 | [12 empty] | FS
693 | [12 empty] | FS
694 | [12 empty] | FS
695 | [12 empty] | FS
696 | [12 empty] | FS
697 | [12 empty] | FS
698 | [12 empty] | FS
699 | [12 empty] | FS
700 | [12 empty] | FS
701 | [12 empty] | FS
702 | [12 empty] | FS
703 | [12 empty] | FS
704 | [12 empty] | FS
705 | [12 empty] | FS
706 | [12 empty] | FS
707 | [12 empty] | FS
708 | [12 empty] | FS
709 | [12 empty] | FS
710 | [12 empty] | FS
711 | [12 empty] | FS
712 | [12 empty] | FS
713 | [12 empty] | FS
714 | [12 empty] | FS
715 | [12 empty] | FS
716 | [12 empty] | FS
717 | [12 empty] | FS
718 | [12 empty] | FS
719 | [12 empty] | FS
720 | [12 empty] | FS
721 | [12 empty] | FS
722 | [12 empty] | FS
723 | [12 empty] | FS
724 | [12 empty] | FS
725 | [12 empty] | FS
726 | [12 empty] | FS
727 | [12 empty] | FS
728 | [12 empty] | FS
729 | [12 empty] | FS
730 | [12 empty] | FS
731 | [12 empty] | FS
732 | [12 empty] | FS
733 | [12 empty] | FS
734 | [12 empty] | FS
735 | [12 empty] | FS
736 | [12 empty] | FS
737 | [12 empty] | FS
738 | [12 empty] | FS
739 | [12 empty] | FS
740 | [12 empty] | FS
741 | [12 empty] | FS
742 | [12 empty] | FS
743 | [12 empty] | FS
744 | [12 empty] | FS
745 | [12 empty] | FS
746 | [12 empty] | FS
747 | [12 empty] | FS
748 | [12 empty] | FS
749 | [12 empty] | FS
750 | [12 empty] | FS
751 | [12 empty] | FS
752 | [12 empty] | FS
753 | [12 empty] | FS
754 | [12 empty] | FS
755 | [12 empty] | FS
756 | [12 empty] | FS
757 | [12 empty] | FS
758 | [12 empty] | FS
759 | [12 empty] | FS
760 | [12 empty] | FS
761 | [12 empty] | FS
762 | [12 empty] | FS
763 | [12 empty] | FS
764 | [12 empty] | FS
765 | [12 empty] | FS
766 | [12 empty] | FS
767 | [12 empty] | FS
768 | [12 empty] | FS
769 | [12 empty] | FS
770 | [12 empty] | FS
771 | [12 empty] | FS
772 | [12 empty] | FS
773 | [12 empty] | FS
774 | [12 empty] | FS
775 | [12 empty] | FS
776 | [12 empty] | FS
777 | [12 empty] | FS
778 | [12 empty] | FS
779 | [12 empty] | FS
780 | [12 empty] | FS
781 | [12 empty] | FS
782 | [12 empty] | FS
783 | [12 empty] | FS
784 | [12 empty] | FS
785 | [12 empty] | FS
786 | [12 empty] | FS
787 | [12 empty] | FS
788 | [12 empty] | FS
789 | [12 empty] | FS
790 | [12 empty] | FS
791 | [12 empty] | FS
792 | [12 empty] | FS
793 | [12 empty] | FS
794 | [12 empty] | FS
795 | [12 empty] | FS
796 | [12 empty] | FS
797 | [12 empty] | FS
798 | [12 empty] | FS
799 | [12 empty] | FS
800 | [12 empty] | FS
801 | [12 empty] | FS
802 | [12 empty] | FS
803 | [12 empty] | FS
804 | [12 empty] | FS
805 | [12 empty] | FS
806 | [12 empty] | FS
807 | [12 empty] | FS
808 | [12 empty] | FS
809 | [12 empty] | FS
810 | [12 empty] | FS
811 | [12 empty] | FS
812 | [12 empty] | FS
813 | [12 empty] | FS

## Settings
Settings
[12 empty] | Gantt | Settings
| Project Details |  |  | Project Role Types |  |  |  | Project Team Management
|  | Project Title: | Task Order 60 Project |  | Role | Code | # |  | Name | Role | Code
[5 empty] | Project Management | PM | 1 |  | GES | Project Management | PM
|  | Project Manager: | B. Prisock |  | Coding | COD | 0 |  | GLOMA | Marketing | MAR
[5 empty] | Design | DES | 0
|  | Project Priority: | Medium |  | Marketing | MAR | 1
[5 empty] | Finance | FIN | 0

## Notes
Proposed Names | Stands For
PlATE | Platform Agnostic Timeline Estimator
CREAP(P) | C2BMC Resiliant Environment Agnostic (Plroject)Planner
FrOSTE | Free Open Source Timeline Estimator
CONG | C2BMC Organizational Normalizing Gantt | C2 Timeline Estiamator Project Planning Env Agnostic
CONG | C2BMC Organized Nerdy Gantt
REAPP | Realtime Env Agnostic Project Planner | C2BMC Realtime Envitonment Agnostic
CREAM | C2BM Realtime Environment Agnostic Manager
Functions: